## Summary
Project | SPTS - Student Performance Tracking System
Module | Total TC | Passed TC | Failed TC | Untested TC | Normal | Abnormal | Boundary | Attachment/Jira Source
Authentication | 9 | 9 | 0 | 0 | 2 | 7 | 0 | SCRUM-8, SCRUM-11, SCRUM-16
Student Management | 15 | 15 | 0 | 0 | 11 | 4 | 0 | SCRUM-21, SCRUM-22
Course / Enrollment Management | 10 | 10 | 0 | 0 | 5 | 5 | 0 | SCRUM-29, SCRUM-31
Grade Entry | 15 | 15 | 0 | 0 | 3 | 4 | 8 | SCRUM-38, SCRUM-42..47
Statistics | 15 | 15 | 0 | 0 | 7 | 5 | 3 | SCRUM-37, SCRUM-40
Code Quality | 1 | 1 | 0 | 0 | 0 | 1 | 0 | SCRUM-32
Alert Controller | 7 | 7 | 0 | 0 | 6 | 0 | 1 | SCRUM-48; AlertControllerTest; JaCoCo 100% line/method coverage
Known Failed / To Fix Next | None
GradeEntry Run Evidence | GradeEntry verification updated: TC_GRADE_05, TC_GRADE_08, TC_GRADE_09, TC_GRADE_10, and TC_GRADE_13 are now passed. Current Grade Entry status: 15 passed, 0 failed.

## Test Cases
TC ID | Module | Title | Precondition | Test Steps | Input / Condition | Expected Result | Actual Result | Priority | N/A/B | Execution Status | Assertion Result | Executed Date | Executed By | Jira / Source | Commit / PR Reference | Attachment Source | Notes
AUTH_API_01 | Authentication | Đăng nhập đúng tài khoản | Người dùng mở Postman/app; có cấu hình auth service | 1. Chuẩn bị input theo case. 2. Gửi request hoặc thao tác login/logout. 3. Kiểm tra HTTP status và response. | POST /api/auth/me hoặc login flow với token hợp lệ | 200 OK + user profile/JWT token |  | High | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-8, SCRUM-11 |  | SCRUM-8_10034_Ph_n t_ch ch_c n_ng _ Thi_t k_ danh s_ch test case.docx
AUTH_API_02 | Authentication | Sai mật khẩu | Người dùng mở Postman/app; có cấu hình auth service | 1. Chuẩn bị input theo case. 2. Gửi request hoặc thao tác login/logout. 3. Kiểm tra HTTP status và response. | Nhập password không đúng | 401 Unauthorized hoặc lỗi credentials |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-8, SCRUM-11 |  | SCRUM-8_10034_Ph_n t_ch ch_c n_ng _ Thi_t k_ danh s_ch test case.docx
AUTH_API_03 | Authentication | Email không tồn tại | Người dùng mở Postman/app; có cấu hình auth service | 1. Chuẩn bị input theo case. 2. Gửi request hoặc thao tác login/logout. 3. Kiểm tra HTTP status và response. | Nhập email chưa có trong hệ thống | 401 Unauthorized hoặc invalid credential |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-8, SCRUM-11 |  | SCRUM-8_10034_Ph_n t_ch ch_c n_ng _ Thi_t k_ danh s_ch test case.docx
AUTH_API_04 | Authentication | Bỏ trống email | Người dùng mở Postman/app; có cấu hình auth service | 1. Chuẩn bị input theo case. 2. Gửi request hoặc thao tác login/logout. 3. Kiểm tra HTTP status và response. | email rỗng | Validation error |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-8, SCRUM-11 |  | SCRUM-8_10034_Ph_n t_ch ch_c n_ng _ Thi_t k_ danh s_ch test case.docx
AUTH_API_05 | Authentication | Bỏ trống password | Người dùng mở Postman/app; có cấu hình auth service | 1. Chuẩn bị input theo case. 2. Gửi request hoặc thao tác login/logout. 3. Kiểm tra HTTP status và response. | password rỗng | Validation error |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-8, SCRUM-11 |  | SCRUM-8_10034_Ph_n t_ch ch_c n_ng _ Thi_t k_ danh s_ch test case.docx
AUTH_API_06 | Authentication | Email sai định dạng | Người dùng mở Postman/app; có cấu hình auth service | 1. Chuẩn bị input theo case. 2. Gửi request hoặc thao tác login/logout. 3. Kiểm tra HTTP status và response. | email không đúng format | Validation error |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-8, SCRUM-11 |  | SCRUM-8_10034_Ph_n t_ch ch_c n_ng _ Thi_t k_ danh s_ch test case.docx
AUTH_API_07 | Authentication | SQL Injection login | Người dùng mở Postman/app; có cấu hình auth service | 1. Chuẩn bị input theo case. 2. Gửi request hoặc thao tác login/logout. 3. Kiểm tra HTTP status và response. | email/password chứa chuỗi ' OR '1'='1 | Không đăng nhập, không bypass auth |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-8, SCRUM-11 |  | SCRUM-8_10034_Ph_n t_ch ch_c n_ng _ Thi_t k_ danh s_ch test case.docx
AUTH_API_08 | Authentication | Đăng xuất hệ thống | Người dùng mở Postman/app; có cấu hình auth service | 1. Chuẩn bị input theo case. 2. Gửi request hoặc thao tác login/logout. 3. Kiểm tra HTTP status và response. | POST /api/auth/logout | 204 No Content và xóa/revoke token |  | High | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-8, SCRUM-11 |  | SCRUM-8_10034_Ph_n t_ch ch_c n_ng _ Thi_t k_ danh s_ch test case.docx
TC_LOGOUT_02 | Authentication | Logout rồi truy cập /me phải trả 401 | Token hợp lệ trước logout | 1. GET /api/auth/me với token hợp lệ. 2. POST /api/auth/logout. 3. GET /api/auth/me lại với token cũ. |  | GET /api/auth/me sau logout trả HTTP 401. | Bug cũ: Expected 401, actual 200; đã fix bằng server-side token revocation. | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-16 | 4091c1a 2026-06-03 Tri2503: fix: SCRUM-16 (#32) | SCRUM-16 Jira description
TC_STUDENT_01 | Student Management | Hiển thị danh sách sinh viên | Admin đã đăng nhập | Mở trang Student Management |  | Hiển thị danh sách sinh viên |  | High | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_02 | Student Management | Thêm sinh viên thành công | Admin đã đăng nhập | Nhập thông tin hợp lệ → Nhấn Save |  | Thêm sinh viên thành công | Screenshot/Jira bug: tạo sinh viên hợp lệ fail trong Postman runner; SCRUM-22 đã xử lý. | High | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-22 | 3f3f608 2026-06-09 gthinh29: hotfix: SCRUM-22 (#45) 4d23215 2026-06-09 gthinh29: hotfix: SCRUM-22 - remove REQUIRES_NEW propagation causing foreign key violation 07e8c0f 2026-06-09 gthinh29: fix: SCRUM-22 (#44) 6e52284 2026-06-09 Tri2503: fix: SCRUM-22 (#37) | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_03 | Student Management | Email sinh viên đã tồn tại | Email tồn tại trong hệ thống | Nhập email trùng |  | Hiển thị lỗi email | Screenshot/Jira bug: hệ thống chưa báo lỗi trùng email đúng; SCRUM-22 đã xử lý. | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-22 | 3f3f608 2026-06-09 gthinh29: hotfix: SCRUM-22 (#45) 4d23215 2026-06-09 gthinh29: hotfix: SCRUM-22 - remove REQUIRES_NEW propagation causing foreign key violation 07e8c0f 2026-06-09 gthinh29: fix: SCRUM-22 (#44) 6e52284 2026-06-09 Tri2503: fix: SCRUM-22 (#37) | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_04 | Student Management | Cập nhật thông tin sinh viên | Sinh viên tồn tại | Sửa thông tin → Nhấn Save |  | Cập nhật thành công |  | High | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_05 | Student Management | Xóa sinh viên | Sinh viên tồn tại | Nhấn Delete |  | Xóa sinh viên thành công | Screenshot/Jira bug: DELETE sinh viên fail; SCRUM-22 đã xử lý. | High | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-22 | 3f3f608 2026-06-09 gthinh29: hotfix: SCRUM-22 (#45) 4d23215 2026-06-09 gthinh29: hotfix: SCRUM-22 - remove REQUIRES_NEW propagation causing foreign key violation 07e8c0f 2026-06-09 gthinh29: fix: SCRUM-22 (#44) 6e52284 2026-06-09 Tri2503: fix: SCRUM-22 (#37) | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_06 | Student Management | Tìm kiếm sinh viên | Sinh viên tồn tại | Nhập tên sinh viên |  | Hiển thị kết quả phù hợp |  | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_07 | Student Management | Xem chi tiết sinh viên | Sinh viên tồn tại | Nhấn View Details |  | Hiển thị đúng thông tin |  | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_08 | Student Management | Bỏ trống thông tin bắt buộc | Admin đã đăng nhập | Để trống dữ liệu → Nhấn Save |  | Hiển thị validation |  | Medium | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_09 | Student Management | Email sai định dạng | Admin đã đăng nhập | Nhập email không hợp lệ |  | Hiển thị lỗi email |  | Medium | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_10 | Student Management | Phân trang danh sách sinh viên | Có nhiều dữ liệu sinh viên | Chuyển trang |  | Hiển thị dữ liệu chính xác |  | Low | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_11 | Student Management | Tính lại điểm GPA | Admin đã đăng nhập | Gửi POST /api/students/{id}/recalculate-gpa |  | GPA được tính lại chính xác |  | Low | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_12 | Student Management | Phân trang danh sách sinh viên | Có nhiều dữ liệu sinh viên | Chuyển sang trang khác |  | Hiển thị dữ liệu chính xác |  | Low | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_13 | Student Management | Lọc sinh viên theo lớp | Có dữ liệu sinh viên | Chọn bộ lọc lớp |  | Hiển thị đúng danh sách sinh viên |  | Low | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_14 | Student Management | Export danh sách sinh viên | Hệ thống có dữ liệu sinh viên | Nhấn nút Export |  | Xuất file danh sách sinh viên thành công |  | Low | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_STUDENT_15 | Student Management | Sinh viên truy cập trang quản lý sinh viên | Sinh viên đã đăng nhập | Truy cập trang Student Management |  | Hệ thống từ chối truy cập |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-18, SCRUM-21 |  | SCRUM-21_10037_TestCases_StudentManagement.docx; SCRUM-22 screenshot for TC02/03/05 | Attachment status: Ready
TC_COURSE_01 | Course / Enrollment Management | Đăng ký môn học thành công | Sinh viên đã đăng nhập | Chọn môn học → Nhấn Đăng ký |  | Đăng ký thành công | Initial run: 400 instead of 201 due offeringId/courseOfferingId mismatch; later screenshot shows 201 Created. | High | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-31 | 9d9dee4 2026-07-03 Tri2503: fix: SCRUM-31 (#49) 7e437c6 2026-06-19 Bruk: fix: SCRUM-31 TC_COURSE_10 (#47) 956f949 2026-06-18 Tri2503: fix: TC_COURSE_01 (SCRUM-31) | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_02 | Course / Enrollment Management | Đăng ký trùng môn | Môn học đã đăng ký | Đăng ký lại môn học |  | Hiển thị lỗi trùng môn |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-28, SCRUM-29 | a61fdc6 2026-06-11 ThanhTunq08: fix: SCRUM-29 b55955e 2026-06-11 Thanh Tung: fix: SCRUM-29 | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_03 | Course / Enrollment Management | Lớp học đã đầy | Lớp học hết chỗ | Chọn đăng ký môn học |  | Hệ thống chặn đăng ký |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-28, SCRUM-29 | a61fdc6 2026-06-11 ThanhTunq08: fix: SCRUM-29 b55955e 2026-06-11 Thanh Tung: fix: SCRUM-29 | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_04 | Course / Enrollment Management | Đăng ký khi chưa đăng nhập | Chưa đăng nhập | Truy cập trang đăng ký |  | Chuyển về trang đăng nhập |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-28, SCRUM-29 | a61fdc6 2026-06-11 ThanhTunq08: fix: SCRUM-29 b55955e 2026-06-11 Thanh Tung: fix: SCRUM-29 | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_05 | Course / Enrollment Management | Hủy đăng ký môn học | Đã đăng ký môn | Nhấn Hủy đăng ký |  | Hủy đăng ký thành công | Initial run: 404 because TC01 did not create a real enrollment id; fixed after TC01 flow corrected. | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-31 | 9d9dee4 2026-07-03 Tri2503: fix: SCRUM-31 (#49) 7e437c6 2026-06-19 Bruk: fix: SCRUM-31 TC_COURSE_10 (#47) 956f949 2026-06-18 Tri2503: fix: TC_COURSE_01 (SCRUM-31) | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_06 | Course / Enrollment Management | Tìm kiếm môn học | Đã đăng nhập | Nhập từ khóa tìm kiếm |  | Hiển thị kết quả phù hợp |  | Low | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-28, SCRUM-29 | a61fdc6 2026-06-11 ThanhTunq08: fix: SCRUM-29 b55955e 2026-06-11 Thanh Tung: fix: SCRUM-29 | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_07 | Course / Enrollment Management | Lọc môn học theo học kỳ | Đã đăng nhập | Chọn học kỳ |  | Hiển thị đúng danh sách |  | Low | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-28, SCRUM-29 | a61fdc6 2026-06-11 ThanhTunq08: fix: SCRUM-29 b55955e 2026-06-11 Thanh Tung: fix: SCRUM-29 | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_08 | Course / Enrollment Management | Trùng lịch học | Có lịch học trùng | Đăng ký môn học mới |  | Hiển thị cảnh báo trùng lịch |  | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-28, SCRUM-29 | a61fdc6 2026-06-11 ThanhTunq08: fix: SCRUM-29 b55955e 2026-06-11 Thanh Tung: fix: SCRUM-29 | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_09 | Course / Enrollment Management | Hiển thị danh sách môn học | Người dùng đã đăng nhập | Mở trang Course |  | Hiển thị đầy đủ danh sách môn học |  | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-28, SCRUM-29 | a61fdc6 2026-06-11 ThanhTunq08: fix: SCRUM-29 b55955e 2026-06-11 Thanh Tung: fix: SCRUM-29 | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_COURSE_10 | Course / Enrollment Management | Đăng ký nhiều môn học | Người dùng đã đăng nhập | Chọn nhiều môn học → Nhấn Đăng ký |  | Endpoint không crash; trả 400 Bad Request nếu không hỗ trợ mảng, hoặc 201 nếu có bulk endpoint hợp lệ. | Initial run: 500 on array body; fixed to reject unsupported array body without crash. | Medium | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-31 | 9d9dee4 2026-07-03 Tri2503: fix: SCRUM-31 (#49) 7e437c6 2026-06-19 Bruk: fix: SCRUM-31 TC_COURSE_10 (#47) 956f949 2026-06-18 Tri2503: fix: TC_COURSE_01 (SCRUM-31) | SCRUM-29 historical CSV; SCRUM-31 screenshots/Jira | Initial Postman run: 10 tests, 7 passed, 3 failed; SCRUM-31 done
TC_GRADE_01 | Grade Entry | Valid_Nominal | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created; Response có trường id; score được lưu đúng; weight được lưu đúng | HTTP 201 Created; assertions passed=4, failed=0 | Medium | N | Passed | 4 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_02 | Grade Entry | Score_Min | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (score = 0.0); score = 0.0 được chấp nhận | HTTP 201 Created; assertions passed=2, failed=0 | Medium | B | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_03 | Grade Entry | Score_MinPlus | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (score = 0.1); score = 0.1 được chấp nhận | HTTP 201 Created; assertions passed=2, failed=0 | Medium | B | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_04 | Grade Entry | Score_MaxMinus | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (score = 9.9); score = 9.9 được chấp nhận | HTTP 201 Created; assertions passed=2, failed=0 | Medium | B | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_05 | Grade Entry | Score_Max | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (score = 10.0); score = 10.0 được chấp nhận | SCRUM-47 Done: score upper boundary accepted. Verified by GradeEntryServiceTest#createGradeEntryAcceptsScoreAtUpperBoundaryAfterExistingEntries. | High | B | Passed | JUnit regression passed | 2026-07-04 | SPTS Testing Team | SCRUM-47 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_06 | Grade Entry | Weight_Min | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (weight = 0.0); weight = 0.0 được chấp nhận | HTTP 201 Created; assertions passed=2, failed=0 | Medium | B | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_07 | Grade Entry | Weight_MinPlus | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (weight = 0.01); weight = 0.01 được chấp nhận | HTTP 201 Created; assertions passed=2, failed=0 | Medium | B | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_08 | Grade Entry | Weight_MaxMinus | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (weight = 0.99); weight = 0.99 được chấp nhận | SCRUM-44 Done: weight max-minus case re-executed and passed after GradeEntry fixes. | High | B | Passed | Re-run passed | 2026-07-04 | SPTS Testing Team | SCRUM-44 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_09 | Grade Entry | Weight_Max | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (weight = 1.0); weight = 1.0 được chấp nhận | SCRUM-46 Done: weight upper boundary accepted. Verified by GradeEntryServiceTest#createGradeEntryAcceptsWeightAtUpperBoundaryAfterExistingEntries. | High | B | Passed | JUnit regression passed | 2026-07-04 | SPTS Testing Team | SCRUM-46 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_10 | Grade Entry | Name_Valid | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (name hợp lệ); name được lưu đúng | SCRUM-45 Done: valid name case re-executed and passed after GradeEntry fixes. | High | N | Passed | Re-run passed | 2026-07-04 | SPTS Testing Team | SCRUM-45 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_11 | Grade Entry | Name_Blank | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 400 Bad Request (name rỗng); Response chứa thông báo lỗi name | HTTP 400 Bad Request; assertions passed=2, failed=0 | Medium | A | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_12 | Grade Entry | Name_TooLong | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 400 Bad Request (name > 100 ký tự); Response chứa thông báo lỗi độ dài | HTTP 400 Bad Request; assertions passed=2, failed=0 | Medium | A | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_13 | Grade Entry | EnrollmentId_Valid | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 201 Created (enrollmentId hợp lệ); enrollmentId được liên kết đúng | SCRUM-43 Done: valid enrollmentId case re-executed and passed after GradeEntry fixes. | High | N | Passed | Re-run passed | 2026-07-04 | SPTS Testing Team | SCRUM-43 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_14 | Grade Entry | EnrollmentId_Null | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 400 Bad Request (enrollmentId null); Response chứa thông báo lỗi enrollmentId | HTTP 400 Bad Request; assertions passed=2, failed=0 | Medium | A | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_GRADE_15 | Grade Entry | EnrollmentId_NotFound | Có enrollment/test data theo pre-request script | 1. Chạy Postman collection SPTS — GradeEntry Blackbox Testing. 2. Gửi POST /api/grade-entries theo case. 3. Kiểm tra status và assertions. |  | Status 404 Not Found (enrollmentId không tồn tại); Response chứa thông báo not found | HTTP 404 Not Found; assertions passed=2, failed=0 | Medium | A | Passed | 2 passed / 0 failed | 2026-07-04 | SPTS Testing Team | SCRUM-38 |  | SCRUM-42_10126_SPTS _ GradeEntry Blackbox Testing.postman_test_run.json; SCRUM-42 screenshot | Run total: 34 assertions, 24 passed, 10 failed.
TC_STAT_01 | Statistics | No_Token | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/dashboard. 2. Input: Không gửi header Authorization. 3. Kiểm tra response theo expected. | Không gửi header Authorization | 401 Unauthorized | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: X3
TC_STAT_02 | Statistics | Invalid_Token | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/dashboard. 2. Input: Authorization: Bearer invalid.fake.token. 3. Kiểm tra response theo expected. | Authorization: Bearer invalid.fake.token | 401 Unauthorized | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: X4
TC_STAT_03 | Statistics | Dashboard_Structure | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/dashboard. 2. Input: Authorization: Bearer <mock-token>. 3. Kiểm tra response theo expected. | Authorization: Bearer <mock-token> | 200 OK — đủ 6 field dữ liệu (topCourses, departmentStats, totalEnrollments, activeEnrollments, completedEnrollments, overallAverageGpa); enrollmentTrends = null, creditDistribution = null (Known Limitation) | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V2,V3,V4
TC_STAT_04 | Statistics | Dashboard_EnrollmentCount | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/dashboard. 2. Input: Authorization: Bearer <mock-token>. 3. Kiểm tra response theo expected. | Authorization: Bearer <mock-token> | 200 OK — totalEnrollments = 90; totalEnrollments ≥ activeEnrollments + completedEnrollments | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V2,V3
TC_STAT_05 | Statistics | Dashboard_GPA_Accuracy | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/dashboard. 2. Input: Authorization: Bearer <mock-token>. 3. Kiểm tra response theo expected. | Authorization: Bearer <mock-token> | 200 OK — overallAverageGpa = trung bình gpaValue ≠ null, làm tròn 2 chữ số thập phân | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V2,V3
TC_STAT_06 | Statistics | Dashboard_TopCourses_In_Dashboard | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/dashboard. 2. Input: Authorization: Bearer <mock-token>. 3. Kiểm tra response theo expected. | Authorization: Bearer <mock-token> | 200 OK — topCourses ≤ 10 phần tử, sorted giảm dần theo totalEnrollments; top 5 seed: SE101, SE301, MAN301, CS202, PHY101 (6 lượt mỗi môn) | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V2,V3
TC_STAT_07 | Statistics | TopCourses_Default_Limit | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/top-courses. 2. Input: Không truyền query param limit (default=10). 3. Kiểm tra response theo expected. | Không truyền query param limit (default=10) | 200 OK — 10 môn, sorted giảm dần theo totalEnrollments | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | B | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V1,V2,V3,B3
TC_STAT_08 | Statistics | TopCourses_Limit_Min | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/top-courses?limit=1. 2. Input: limit=1. 3. Kiểm tra response theo expected. | limit=1 | 200 OK — đúng 1 phần tử (môn có totalEnrollments cao nhất) | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | B | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V1,V2,V3,B1
TC_STAT_09 | Statistics | TopCourses_Limit_Two | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/top-courses?limit=2. 2. Input: limit=2. 3. Kiểm tra response theo expected. | limit=2 | 200 OK — đúng 2 phần tử, cùng totalEnrollments=6 | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | B | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V1,V2,V3,B2
TC_STAT_10 | Statistics | TopCourses_Limit_Zero | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/top-courses?limit=0. 2. Input: limit=0. 3. Kiểm tra response theo expected. | limit=0 | 200 OK — array rỗng [] | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: X1,V2
TC_STAT_11 | Statistics | TopCourses_InvalidType | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/top-courses?limit=abc. 2. Input: limit=abc (chuỗi không parse được thành int). 3. Kiểm tra response theo expected. | limit=abc (chuỗi không parse được thành int) | 400 Bad Request — lỗi parse kiểu int | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: X2,V2
TC_STAT_12 | Statistics | Departments_Structure_And_Data | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/departments. 2. Input: Authorization: Bearer <mock-token>. 3. Kiểm tra response theo expected. | Authorization: Bearer <mock-token> | 200 OK — 5 department (chỉ dept có offering); sorted giảm dần theo totalEnrollments | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V2,V3
TC_STAT_13 | Statistics | Departments_UniqueStudents_Count | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/departments. 2. Input: Authorization: Bearer <mock-token>. 3. Kiểm tra response theo expected. | Authorization: Bearer <mock-token> | 200 OK — totalStudents = đếm distinct studentId (không đếm trùng khi 1 SV học nhiều môn cùng dept) | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V2,V3,X5
TC_STAT_14 | Statistics | EnrollmentTrends_SinglePeriod | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/enrollment-trends. 2. Input: Authorization: Bearer <mock-token>. 3. Kiểm tra response theo expected. | Authorization: Bearer <mock-token> | 200 OK — đúng 1 phần tử: semester=SPRING, academicYear=2026, period="Spring 2026", enrollmentCount=90 | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V2,V3
TC_STAT_15 | Statistics | CreditDist_AllGroups | Token/DB theo attachment Statistics; dev profile allow mock token | 1. Gửi GET /api/statistics/credit-distribution. 2. Input: Authorization: Bearer <mock-token>. 3. Kiểm tra response theo expected. | Authorization: Bearer <mock-token> | 200 OK — 4 nhóm credits {1,3,4,5}, sorted tăng dần; tổng courseCount = 20 | Screenshot 2026-07-03: 27 assertions, all green/passed. | Medium | N | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-37, SCRUM-40 |  | SCRUM-40_10117_KichBan_KiemThu_Statistics_.docx; SCRUM-37 screenshots | Tag: V2,V3
TC_CODE_01 | Code Quality | Sonar rule typescript:S7767 không còn cảnh báo bitwise truncate | Source frontend hiện tại | 1. Kiểm tra CourseProposalModal.tsx. 2. Chạy lại SonarQube hoặc build/test liên quan. | frontend/src/components/CourseProposalModal.tsx | Không còn dùng ¦= 0 để truncate; dùng Math.trunc(). Sonar không còn cảnh báo S7767. | Đã fix lỗi S7767 và không còn hiển thị lỗi trên Sonar. | High | A | Passed |  | 2026-07-04 | SPTS Testing Team | SCRUM-32 | ba82807 2026-06-21 teohoan: fix: SCRUM-32 (#48) a4c5c89 2026-06-19 teohoan: fix: replace bitwise ¦=0 with Math.trunc in generateCourseCode (SCRUM-32) | SCRUM-32 Jira screenshots/comments
TC_ALERT_WB_01 | Alert Controller | Get all alerts | AlertService được mock; có dữ liệu cảnh báo mẫu | 1. Chạy JUnit MockMvc test. 2. Gọi endpoint AlertController tương ứng. 3. Kiểm tra HTTP status, response body và service delegation. | GET /api/alerts | HTTP 200; trả danh sách AlertDTO | Passed: response id=1, level=WARNING | High | N | Passed | JUnit passed | 2026-07-10 | Bruk | SCRUM-48 | 97ee75a fix: SCRUM-48 | backend/jacoco-report/com.spts.controller/AlertController.html | Tags: A1, V1, B1
TC_ALERT_WB_02 | Alert Controller | Get alert by ID | AlertService.getAlertById(1) trả AlertDTO | 1. Chạy JUnit MockMvc test. 2. Gọi endpoint AlertController tương ứng. 3. Kiểm tra HTTP status, response body và service delegation. | GET /api/alerts/1 | HTTP 200; trả AlertDTO có id=1 | Passed: response id=1, type=LOW_GPA | High | N | Passed | JUnit passed | 2026-07-10 | Bruk | SCRUM-48 | 97ee75a fix: SCRUM-48 | backend/jacoco-report/com.spts.controller/AlertController.html | Tags: A2, V1, B1
TC_ALERT_WB_03 | Alert Controller | Create alert | Request body AlertDTO hợp lệ | 1. Chạy JUnit MockMvc test. 2. Gọi endpoint AlertController tương ứng. 3. Kiểm tra HTTP status, response body và service delegation. | POST /api/alerts với JSON hợp lệ | HTTP 201; trả alert vừa tạo | Passed: response id=1, studentId=53 | High | N | Passed | JUnit passed | 2026-07-10 | Bruk | SCRUM-48 | 97ee75a fix: SCRUM-48 | backend/jacoco-report/com.spts.controller/AlertController.html | Tags: A3, V1, B1
TC_ALERT_WB_04 | Alert Controller | Update alert | Alert tồn tại; request body AlertDTO hợp lệ | 1. Chạy JUnit MockMvc test. 2. Gọi endpoint AlertController tương ứng. 3. Kiểm tra HTTP status, response body và service delegation. | PUT /api/alerts/1 với message cập nhật | HTTP 200; message được cập nhật | Passed: message=Updated warning | High | N | Passed | JUnit passed | 2026-07-10 | Bruk | SCRUM-48 | 97ee75a fix: SCRUM-48 | backend/jacoco-report/com.spts.controller/AlertController.html | Tags: A4, V1, B1
TC_ALERT_WB_05 | Alert Controller | Delete alert | Alert ID hợp lệ | 1. Chạy JUnit MockMvc test. 2. Gọi endpoint AlertController tương ứng. 3. Kiểm tra HTTP status, response body và service delegation. | DELETE /api/alerts/1 | HTTP 204; gọi AlertService.deleteAlert(1) | Passed: service method verified | High | N | Passed | JUnit passed | 2026-07-10 | Bruk | SCRUM-48 | 97ee75a fix: SCRUM-48 | backend/jacoco-report/com.spts.controller/AlertController.html | Tags: A5, V1, B1
TC_ALERT_WB_06 | Alert Controller | State change endpoints | Alert IDs hợp lệ; resolvedBy=ADMIN; batch body [1,2] | 1. Chạy JUnit MockMvc test. 2. Gọi endpoint AlertController tương ứng. 3. Kiểm tra HTTP status, response body và service delegation. | PUT read/resolve/batch/read/batch/resolve/student/{id}/read-all | HTTP 200; trả alert/count đúng | Passed: read=true, resolved=true, count=2/3 | High | N | Passed | JUnit passed | 2026-07-10 | Bruk | SCRUM-48 | 97ee75a fix: SCRUM-48 | backend/jacoco-report/com.spts.controller/AlertController.html | Tags: A6-A10, V2, B2
TC_ALERT_WB_07 | Alert Controller | Query endpoints and coverage percent | AlertService query methods được mock; summary có count mẫu | 1. Chạy JUnit MockMvc test. 2. Gọi endpoint AlertController tương ứng. 3. Kiểm tra HTTP status, response body và service delegation. | GET unread/unresolved/urgent/student/level/type/count/summary | HTTP 200; body đúng shape; JaCoCo line/method coverage 100% | Passed: 19/19 endpoint methods; 23/23 lines; 20/20 methods | High | B | Passed | JUnit + JaCoCo passed | 2026-07-10 | Bruk | SCRUM-48 | 97ee75a fix: SCRUM-48 | backend/jacoco-report/com.spts.controller/AlertController.html | Tags: A11-A19, V3, V4, B3, B4

## Function Auth
Function Code | AUTH |  |  | Function Name | Authentication
Created By | SPTS Team |  |  | Executed By | SPTS Testing Team
Lines of code |  | 100 |  | Lack of test cases | [5 empty] | 0
Test requirement | SCRUM-8 authentication scenarios + SCRUM-16 logout bug verification
Passed |  | Failed |  | Untested | [5 empty] | N/A/B |  |  | Total Test Cases
9 |  | 0 |  | 0 | [5 empty] | 2 | 7 | 0 | 9
|  |  |  | AUTH_API_01 | AUTH_API_02 | AUTH_API_03 | AUTH_API_04 | AUTH_API_05 | AUTH_API_06 | AUTH_API_07 | AUTH_API_08 | TC_LOGOUT_02
Condition | Precondition
|  |  | Đăng nhập đúng tài khoản | O
|  |  | Sai mật khẩu |  | O
|  |  | Email không tồn tại |  |  | O
|  |  | Bỏ trống email |  |  |  | O
|  |  | Bỏ trống password |  |  |  |  | O
|  |  | Email sai định dạng | [5 empty] | O
|  |  | SQL Injection login | [6 empty] | O
|  |  | Đăng xuất hệ thống | [7 empty] | O
|  |  | Logout rồi truy cập /me phải trả 401 | [8 empty] | O
Confirm | Return
|  |  | 200 OK | O
|  |  | 401 Unauthorized |  | O | O | [5 empty] | O
|  |  | Expected passed behavior |  |  |  | O | O | O | O
|  |  | 204 No Content | [7 empty] | O
Exception
Log message
|  |  | 200 OK + user profile/JWT token | O
|  |  | 401 Unauthorized hoặc lỗi credentials |  | O
|  |  | 401 Unauthorized hoặc invalid credential |  |  | O
|  |  | Validation error |  |  |  | O
|  |  | Validation error |  |  |  |  | O
|  |  | Validation error | [5 empty] | O
|  |  | Không đăng nhập, không bypass auth | [6 empty] | O
|  |  | 204 No Content và xóa/revoke token | [7 empty] | O
|  |  | Bug cũ: Expected 401, actual 200; đã fix bằng server-side token revocation. | [8 empty] | O
Result | Type(N : Normal, A : Abnormal, B : Boundary) |  |  | N | A | A | A | A | A | A | N | A
| Passed/Failed |  |  | P | P | P | P | P | P | P | P | P
| Executed Date |  |  | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04
| Defect ID |  |  | SCRUM-8, SCRUM-11 | SCRUM-8, SCRUM-11 | SCRUM-8, SCRUM-11 | SCRUM-8, SCRUM-11 | SCRUM-8, SCRUM-11 | SCRUM-8, SCRUM-11 | SCRUM-8, SCRUM-11 | SCRUM-8, SCRUM-11 | SCRUM-16

## Function Student
Function Code | STUDENT |  |  | Function Name | Student Management
Created By | SPTS Team |  |  | Executed By | SPTS Testing Team
Lines of code |  | 100 |  | Lack of test cases | [5 empty] | 0
Test requirement | SCRUM-21 StudentManagement DOCX: TC_STUDENT_01..15 + SCRUM-22 bug evidence
Passed |  | Failed |  | Untested | [5 empty] | N/A/B |  |  | Total Test Cases
15 |  | 0 |  | 0 | [5 empty] | 11 | 4 | 0 | 15
|  |  |  | TC_STUDENT_01 | TC_STUDENT_02 | TC_STUDENT_03 | TC_STUDENT_04 | TC_STUDENT_05 | TC_STUDENT_06 | TC_STUDENT_07 | TC_STUDENT_08 | TC_STUDENT_09 | TC_STUDENT_10 | TC_STUDENT_11 | TC_STUDENT_12 | TC_STUDENT_13 | TC_STUDENT_14 | TC_STUDENT_15
Condition | Precondition
|  |  | Hiển thị danh sách sinh viên | O
|  |  | Thêm sinh viên thành công |  | O
|  |  | Email sinh viên đã tồn tại |  |  | O
|  |  | Cập nhật thông tin sinh viên |  |  |  | O
|  |  | Xóa sinh viên |  |  |  |  | O
|  |  | Tìm kiếm sinh viên | [5 empty] | O
|  |  | Xem chi tiết sinh viên | [6 empty] | O
|  |  | Bỏ trống thông tin bắt buộc | [7 empty] | O
|  |  | Email sai định dạng | [8 empty] | O
|  |  | Phân trang danh sách sinh viên | [9 empty] | O
|  |  | Tính lại điểm GPA | [10 empty] | O
|  |  | Phân trang danh sách sinh viên | [11 empty] | O
|  |  | Lọc sinh viên theo lớp | [12 empty] | O
|  |  | Export danh sách sinh viên | [13 empty] | O
|  |  | Sinh viên truy cập trang quản lý sinh viên | [14 empty] | O
Confirm | Return
|  |  | Expected passed behavior | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
Exception
Log message
|  |  | Hiển thị danh sách sinh viên | O
|  |  | Screenshot/Jira bug: tạo sinh viên hợp lệ fail trong Postman runner; SCRUM-22 đã xử lý. |  | O
|  |  | Screenshot/Jira bug: hệ thống chưa báo lỗi trùng email đúng; SCRUM-22 đã xử lý. |  |  | O
|  |  | Cập nhật thành công |  |  |  | O
|  |  | Screenshot/Jira bug: DELETE sinh viên fail; SCRUM-22 đã xử lý. |  |  |  |  | O
|  |  | Hiển thị kết quả phù hợp | [5 empty] | O
|  |  | Hiển thị đúng thông tin | [6 empty] | O
|  |  | Hiển thị validation | [7 empty] | O
|  |  | Hiển thị lỗi email | [8 empty] | O
|  |  | Hiển thị dữ liệu chính xác | [9 empty] | O
|  |  | GPA được tính lại chính xác | [10 empty] | O
|  |  | Hiển thị dữ liệu chính xác | [11 empty] | O
|  |  | Hiển thị đúng danh sách sinh viên | [12 empty] | O
|  |  | Xuất file danh sách sinh viên thành công | [13 empty] | O
|  |  | Hệ thống từ chối truy cập | [14 empty] | O
Result | Type(N : Normal, A : Abnormal, B : Boundary) |  |  | N | N | A | N | N | N | N | A | A | N | N | N | N | N | A
| Passed/Failed |  |  | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
| Executed Date |  |  | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04
| Defect ID |  |  | SCRUM-18, SCRUM-21 | SCRUM-22 | SCRUM-22 | SCRUM-18, SCRUM-21 | SCRUM-22 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21 | SCRUM-18, SCRUM-21

## Function Course
Function Code | COURSE |  |  | Function Name | Course / Enrollment Management
Created By | SPTS Team |  |  | Executed By | SPTS Testing Team
Lines of code |  | 100 |  | Lack of test cases | [5 empty] | 0
Test requirement | SCRUM-29 TC_COURSE_01..10 + SCRUM-31 bug screenshots/Jira
Passed |  | Failed |  | Untested | [5 empty] | N/A/B |  |  | Total Test Cases
10 |  | 0 |  | 0 | [5 empty] | 5 | 5 | 0 | 10
|  |  |  | TC_COURSE_01 | TC_COURSE_02 | TC_COURSE_03 | TC_COURSE_04 | TC_COURSE_05 | TC_COURSE_06 | TC_COURSE_07 | TC_COURSE_08 | TC_COURSE_09 | TC_COURSE_10
Condition | Precondition
|  |  | Đăng ký môn học thành công | O
|  |  | Đăng ký trùng môn |  | O
|  |  | Lớp học đã đầy |  |  | O
|  |  | Đăng ký khi chưa đăng nhập |  |  |  | O
|  |  | Hủy đăng ký môn học |  |  |  |  | O
|  |  | Tìm kiếm môn học | [5 empty] | O
|  |  | Lọc môn học theo học kỳ | [6 empty] | O
|  |  | Trùng lịch học | [7 empty] | O
|  |  | Hiển thị danh sách môn học | [8 empty] | O
|  |  | Đăng ký nhiều môn học | [9 empty] | O
Confirm | Return
|  |  | Expected passed behavior | O | O | O | O | O | O | O | O | O
|  |  | 400 Bad Request | [9 empty] | O
Exception
Log message
|  |  | Initial run: 400 instead of 201 due offeringId/courseOfferingId mismatch; later screenshot shows 201 Created. | O
|  |  | Hiển thị lỗi trùng môn |  | O
|  |  | Hệ thống chặn đăng ký |  |  | O
|  |  | Chuyển về trang đăng nhập |  |  |  | O
|  |  | Initial run: 404 because TC01 did not create a real enrollment id; fixed after TC01 flow corrected. |  |  |  |  | O
|  |  | Hiển thị kết quả phù hợp | [5 empty] | O
|  |  | Hiển thị đúng danh sách | [6 empty] | O
|  |  | Hiển thị cảnh báo trùng lịch | [7 empty] | O
|  |  | Hiển thị đầy đủ danh sách môn học | [8 empty] | O
|  |  | Initial run: 500 on array body; fixed to reject unsupported array body without crash. | [9 empty] | O
Result | Type(N : Normal, A : Abnormal, B : Boundary) |  |  | N | A | A | A | N | N | N | A | N | A
| Passed/Failed |  |  | P | P | P | P | P | P | P | P | P | P
| Executed Date |  |  | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04
| Defect ID |  |  | SCRUM-31 | SCRUM-28, SCRUM-29 | SCRUM-28, SCRUM-29 | SCRUM-28, SCRUM-29 | SCRUM-31 | SCRUM-28, SCRUM-29 | SCRUM-28, SCRUM-29 | SCRUM-28, SCRUM-29 | SCRUM-28, SCRUM-29 | SCRUM-31

## Function Grade
Function Code | GRADE |  |  | Function Name | Grade Entry
Created By | SPTS Team |  |  | Executed By | SPTS Testing Team
Lines of code |  | 100 |  | Lack of test cases | [5 empty] | 0
Test requirement | SCRUM-42 GradeEntry bug cases all re-verified: TC_GRADE_01..15 passed
Passed |  | Failed |  | Untested | [5 empty] | N/A/B |  |  | Total Test Cases
15 |  | 0 |  | 0 | [5 empty] | 3 | 4 | 8 | 15
|  |  |  | TC_GRADE_01 | TC_GRADE_02 | TC_GRADE_03 | TC_GRADE_04 | TC_GRADE_05 | TC_GRADE_06 | TC_GRADE_07 | TC_GRADE_08 | TC_GRADE_09 | TC_GRADE_10 | TC_GRADE_11 | TC_GRADE_12 | TC_GRADE_13 | TC_GRADE_14 | TC_GRADE_15
Condition | Precondition
|  |  | Valid_Nominal | O
|  |  | Score_Min |  | O
|  |  | Score_MinPlus |  |  | O
|  |  | Score_MaxMinus |  |  |  | O
|  |  | Score_Max |  |  |  |  | O
|  |  | Weight_Min | [5 empty] | O
|  |  | Weight_MinPlus | [6 empty] | O
|  |  | Weight_MaxMinus | [7 empty] | O
|  |  | Weight_Max | [8 empty] | O
|  |  | Name_Valid | [9 empty] | O
|  |  | Name_Blank | [10 empty] | O
|  |  | Name_TooLong | [11 empty] | O
|  |  | EnrollmentId_Valid | [12 empty] | O
|  |  | EnrollmentId_Null | [13 empty] | O
|  |  | EnrollmentId_NotFound | [14 empty] | O
Confirm | Return
|  |  | 201 Created | O | O | O | O | O | O | O | O | O | O |  |  | O
|  |  | 400 Bad Request | [10 empty] | O | O |  | O
|  |  | 404 Not Found | [14 empty] | O
Exception
Log message
|  |  | HTTP 201 Created; assertions passed=4, failed=0 | O
|  |  | HTTP 201 Created; assertions passed=2, failed=0 |  | O
|  |  | HTTP 201 Created; assertions passed=2, failed=0 |  |  | O
|  |  | HTTP 201 Created; assertions passed=2, failed=0 |  |  |  | O
|  |  | SCRUM-47 Done; GradeEntryServiceTest score upper boundary regression passed. |  |  |  |  | O
|  |  | HTTP 201 Created; assertions passed=2, failed=0 | [5 empty] | O
|  |  | HTTP 201 Created; assertions passed=2, failed=0 | [6 empty] | O
|  |  | HTTP 500 Internal Server Error; assertions passed=0, failed=2. Unresolved server-side bug from SCRUM-42. | [7 empty] | SCRUM-44 Done; weight max-minus re-run passed.
|  |  | SCRUM-46 Done; GradeEntryServiceTest weight upper boundary regression passed. | [8 empty] | O
|  |  | HTTP 500 Internal Server Error; assertions passed=0, failed=2. Unresolved server-side bug from SCRUM-42. | [9 empty] | SCRUM-45 Done; valid name re-run passed.
|  |  | HTTP 400 Bad Request; assertions passed=2, failed=0 | [10 empty] | O
|  |  | HTTP 400 Bad Request; assertions passed=2, failed=0 | [11 empty] | O
|  |  | HTTP 404 Not Found; assertions passed=0, failed=2. Unresolved server-side bug from SCRUM-42. | [12 empty] | SCRUM-43 Done; valid enrollmentId re-run passed.
|  |  | HTTP 400 Bad Request; assertions passed=2, failed=0 | [13 empty] | O
|  |  | HTTP 404 Not Found; assertions passed=2, failed=0 | [14 empty] | O
Result | Type(N : Normal, A : Abnormal, B : Boundary) |  |  | N | B | B | B | B | B | B | B | B | N | A | A | N | A | A
| Passed/Failed |  |  | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
| Executed Date |  |  | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04
| Defect ID |  |  | SCRUM-38 | SCRUM-38 | SCRUM-38 | SCRUM-38 | SCRUM-47 | SCRUM-38 | SCRUM-38 | SCRUM-44 | SCRUM-46 | SCRUM-45 | SCRUM-38 | SCRUM-38 | SCRUM-43 | SCRUM-38 | SCRUM-38

## Function Stats
Function Code | STAT |  |  | Function Name | Statistics
Created By | SPTS Team |  |  | Executed By | SPTS Testing Team
Lines of code |  | 100 |  | Lack of test cases | [5 empty] | 0
Test requirement | SCRUM-40 DOCX: TC_STAT_01..15 + SCRUM-37 screenshots
Passed |  | Failed |  | Untested | [5 empty] | N/A/B |  |  | Total Test Cases
15 |  | 0 |  | 0 | [5 empty] | 7 | 5 | 3 | 15
|  |  |  | TC_STAT_01 | TC_STAT_02 | TC_STAT_03 | TC_STAT_04 | TC_STAT_05 | TC_STAT_06 | TC_STAT_07 | TC_STAT_08 | TC_STAT_09 | TC_STAT_10 | TC_STAT_11 | TC_STAT_12 | TC_STAT_13 | TC_STAT_14 | TC_STAT_15
Condition | Precondition
|  |  | No_Token | O
|  |  | Invalid_Token |  | O
|  |  | Dashboard_Structure |  |  | O
|  |  | Dashboard_EnrollmentCount |  |  |  | O
|  |  | Dashboard_GPA_Accuracy |  |  |  |  | O
|  |  | Dashboard_TopCourses_In_Dashboard | [5 empty] | O
|  |  | TopCourses_Default_Limit | [6 empty] | O
|  |  | TopCourses_Limit_Min | [7 empty] | O
|  |  | TopCourses_Limit_Two | [8 empty] | O
|  |  | TopCourses_Limit_Zero | [9 empty] | O
|  |  | TopCourses_InvalidType | [10 empty] | O
|  |  | Departments_Structure_And_Data | [11 empty] | O
|  |  | Departments_UniqueStudents_Count | [12 empty] | O
|  |  | EnrollmentTrends_SinglePeriod | [13 empty] | O
|  |  | CreditDist_AllGroups | [14 empty] | O
Confirm | Return
|  |  | 401 Unauthorized | O | O
|  |  | 200 OK |  |  | O | O | O | O | O | O | O | O |  | O | O | O | O
|  |  | 400 Bad Request | [10 empty] | O
Exception
Log message
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. |  | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. |  |  | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. |  |  |  | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. |  |  |  |  | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [5 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [6 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [7 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [8 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [9 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [10 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [11 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [12 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [13 empty] | O
|  |  | Screenshot 2026-07-03: 27 assertions, all green/passed. | [14 empty] | O
Result | Type(N : Normal, A : Abnormal, B : Boundary) |  |  | A | A | N | N | N | N | B | B | B | A | A | N | A | N | N
| Passed/Failed |  |  | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
| Executed Date |  |  | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04 | 2026-07-04
| Defect ID |  |  | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40 | SCRUM-37, SCRUM-40

## Function Quality
Function Code | QUALITY |  |  | Function Name | Code Quality
Created By | SPTS Team |  |  | Executed By | SPTS Testing Team
Lines of code |  | 100 |  | Lack of test cases |  | 0
Test requirement | SCRUM-32 Sonar S7767 fix
Passed |  | Failed |  | Untested |  | N/A/B |  |  | Total Test Cases
1 |  | 0 |  | 0 |  | 0 | 1 | 0 | 1
TC_CODE_01
Condition | Precondition
|  |  | Sonar rule typescript:S7767 không còn cảnh báo bitwise truncate | O
Confirm | Return
|  |  | Expected passed behavior | O
Exception
Log message
|  |  | Đã fix lỗi S7767 và không còn hiển thị lỗi trên Sonar. | O
Result | Type(N : Normal, A : Abnormal, B : Boundary) |  |  | A
| Passed/Failed |  |  | P
| Executed Date |  |  | 2026-07-04
| Defect ID |  |  | SCRUM-32

## CI Coverage
Jira Key | Test Case ID | Area | Automated test / command | CI | Jira Status | Notes
SCRUM-16 | TC_LOGOUT_02 | Authentication | backend: AuthControllerTest#testGetMeAfterLogoutReturns401 via mvn -B test -Dfirebase.enabled=false | Yes | Done | Server-side logout token revocation regression.
SCRUM-31 | TC_COURSE_10 | Course / Enrollment Management | backend: EnrollmentControllerTest#createEnrollmentRejectsArrayRequestBody via mvn -B test -Dfirebase.enabled=false | Yes | Done | Unsupported array body now returns 400 instead of 500.
SCRUM-32 | TC_CODE_01 | Code Quality | Manual Sonar/build evidence; frontend Vitest is not enforced in CI until existing frontend tests are fixed | No | Done | Jira is Done, but no passing CI regression is added for this item in this update.
SCRUM-46 | TC_GRADE_09 | Grade Entry | backend: GradeEntryServiceTest#createGradeEntryAcceptsWeightAtUpperBoundaryAfterExistingEntries via mvn -B test -Dfirebase.enabled=false | Yes | Done | Weight upper boundary 1.0 accepted.
SCRUM-47 | TC_GRADE_05 | Grade Entry | backend: GradeEntryServiceTest#createGradeEntryAcceptsScoreAtUpperBoundaryAfterExistingEntries via mvn -B test -Dfirebase.enabled=false | Yes | Done | Score upper boundary 10.0 accepted.
SCRUM-42 | TC_GRADE_08 | Grade Entry | Not included as passing CI regression yet | No | Done | Passed in latest GradeEntry verification; no dedicated CI regression recorded yet.
SCRUM-42 | TC_GRADE_10 | Grade Entry | Not included as passing CI regression yet | No | Done | Passed in latest GradeEntry verification; no dedicated CI regression recorded yet.
SCRUM-42 | TC_GRADE_13 | Grade Entry | Not included as passing CI regression yet | No | Done | Passed in latest GradeEntry verification; no dedicated CI regression recorded yet.
SCRUM-11 | AUTH_API_* | Authentication | Frontend auth Vitest files exist, but npm run test:run currently has unrelated failures; keep manual until green | No | Done | Jira is Done; not added as a required CI check because current frontend suite fails locally.
SCRUM-48 | TC_ALERT_WB_01..07 | Alert Controller | backend: AlertControllerTest via mvn test jacoco:report -Dtest=AlertControllerTest; JaCoCo 126/126 instructions, 23/23 lines, 20/20 methods | Yes | Done | White-box controller coverage: 19/19 endpoint methods covered, line/method coverage 100%.